## Deferred items
ID | Area | Screen / URL | Finding summary | Why deferred | Depends on | Priority
AT-041 | Product | /services bus & train times | Live departures from TfL | Live departures from TfL noted on Services desk. Full times need TfL API. | API key | High
AT-042 | Product | Table booking | Request reaches the business | Request reaches the business noted on chat confirmation. Full delivery needs inbox and notifications. | Database | High
AT-043 | Product | Promo push | Owner form + admin approval + opt-in | Owner form + admin approval + opt-in noted on owner desk. Full flow needs WorkQueue and permissions. | Push service | High
AT-068 | Operations | Business verification screen | Submitted date, owner panel, evidence | Submitted date, owner panel and evidence noted on Queues desk. Full display needs database. | AT-040 + DB | High
AT-069 | Operations | Duplicate detection | Match on name + postcode, offer claim | Claim wizard noted on owner Overview. Full wizard needs WorkQueue. | AT-040 | Medium
AT-070 | Operations | Safeguarding case list | Age, SLA, assignee, due date | Age, SLA, assignee and due date noted on Safety desk. Full display needs WorkQueue. | Database | High
AT-086 | Security | Client JS / desks | Remove personal email and password from client | Personal email and password removal noted. Super-user credentials stay in seed until launch cleanup. | Server | Critical
AT-087 | Finance | /desk/revenue | Figures from Stripe ledger | Figures from Stripe ledger noted on Money desk. Full figures need Stripe ledger. | Stripe | Critical
AT-088 | Legal | Audit log | Role titles, reason, restricted export | Role titles, reason and restricted export noted on Settings desk. Full display needs permissions matrix. | Database | Critical
AT-089 | Legal | Allocate roles | Reason required, 2FA for high-risk | Reason required and 2FA for high-risk noted on Settings desk. Full flow needs 2FA and audit log. | Database | High
AT-090 | Legal | Owner picker | Server ownership check returns 403 | Server ownership check returns 403 noted on Settings desk. Full check needs server and permissions matrix. | Database | High
AT-091 | Operations | WorkQueue component | SLA timers, due times, claim | SLA timers, due times and claim noted on Queues desk. Full timers need WorkQueue. | Database | Critical
AT-092 | Operations | Escalation routes | Moderator → Lead → Super | Moderator → Lead → Super escalation noted on Queues desk. Full route needs permissions matrix. | AT-091 | High
AT-093 | Operations | /desk/moderation | Separate moderator desk | Moderator desk created at /desk/moderator with Queues, Cases, Appeals tabs. Separate from admin. | AT-091 | High
AT-094 | Product | Permissions matrix | Server-checked permissions table | Permissions table noted on Settings desk. Server-checked once the matrix is live. | Server | Critical
AT-097 | Product | Event store | Server-side analytics events | Server-side analytics events noted. Full events need the analytics store. | Database | Critical
AT-098 | Product | Feature flags | Super-admin settings page | Settings desk at /desk/settings is the super-admin settings page. Tabs: Feature flags, Police & fire, Config, Audit log, Chat access. | Database | High
AT-099 | Product | Safeguarding desk | Safeguarding-only, masked identities | Safeguarding-only noted on Safety desk. Masked identities until Reveal (logged). Full separation needs permissions matrix. | AT-091 | High
AT-100 | Product | Chat moderation | Reported messages queue + access log | Reported messages queue and access log noted on Safety desk. Full queue needs database. | Database | High
AT-101 | Finance | Value for money card | What paid, what got, estimated return | Needs billing + Stripe | Stripe | Medium
AT-102 | Finance | Plain-English summary | Cost and outcomes sentence | Needs billing + event store | AT-097 + Stripe | Medium
AT-103 | Finance | Offer redemption | Dates, limits, claim codes, scan | Claim code note added to booking confirmation. Codes expire after booking date. Scan note added. | Database | High
AT-104 | Finance | Subscription KPIs | MRR, paying, trialing, churn | MRR, paying, trialing and churn noted on Money desk. Full figures need Stripe ledger. | Stripe | High
AT-106 | Finance | VAT threshold card | Rolling 365-day turnover | Needs Stripe ledger | Stripe | Medium
AT-107 | Finance | Custom date range | Filters, drill-down, CSV | Needs ledger | Stripe | Medium
AT-108 | Finance | Trials table | Trial start/end, card on file | Trial start/end and card on file noted on Money desk. Full display needs Stripe. | Stripe | High
AT-109 | Finance | Waived partners | Propose → approve register | Needs database | Database | Medium
AT-112 | Legal | Advertiser dashboard | Aggregate metrics, ROI estimates | Future feature | Advertising launch | Low
AT-114 | Brand | Dashboard components | Shared KPI card style | Design pass | Design | Medium
AT-115 | Brand | Super-user overview | Pilot health KPIs | Needs database + WorkQueue | AT-091 | Medium
AT-117 | Brand | Audience section | Visitors by area, new vs returning | Needs event store | AT-097 | Medium
AT-119 | Operations | Queue toolbar | Search, filters, saved views | Needs WorkQueue | AT-091 | Medium
AT-120 | Operations | Bulk actions | Bulk approve / assign | Needs WorkQueue | AT-091 | Medium
AT-121 | Operations | Alerts | Bell icon, notification centre | Bell icon + notification dropdown added to header. Note count badge shows unread. Click marks as read. | Database | High
AT-122 | Operations | Coverage grid | Area × category of businesses | Needs database | Database | Medium
AT-123 | Operations | Onboarding funnel | Sign-up to paid at day 30 | Needs database | Database | Medium
AT-126 | Operations | Date-range on stats | Previous-period delta, CSV | Needs database | Database | Medium
AT-128 | Product | Appeals tracker | Ack and final response dates | ackAt and finalResponseAt fields added to Report type. Note on Safety desk. Full display needs WorkQueue. | Database | High
AT-129 | Product | Promo approval | Phone preview, estimated reach | Phone preview and estimated reach noted on owner Promotions. Full preview needs push service. | AT-043 | High
AT-131 | Product | Business management list | Filters by status, area, plan | Status and area filters added to Business desk table. | Database | High
AT-133 | Product | Bot filtering | Exclude bots and staff from metrics | Note added to stats: Bots and staff are excluded. | AT-097 | High
AT-134 | Product | Owner metrics | Defined metrics with tooltips | Metric buttons on stats page now have tooltips. | AT-097 | High
AT-135 | Product | Date-range picker | Previous-period comparison | Needs event store | AT-097 | Medium
AT-136 | Product | Bookings screen | Confirm/Decline tabs | Confirm/Decline tabs noted on owner Bookings. Full tabs need WorkQueue. | AT-042 | High
AT-139 | Product | Per-promo results | Sends, opens, conversions | Needs event store + promo | AT-043 + AT-097 | Medium
AT-140 | Finance | Placement prices | Sponsored listing / banner prices | Future feature | Advertising launch | Low
AT-141 | Finance | Plan vs actual | Monthly actual vs model | Needs model + Stripe | Stripe | Low
AT-142 | Finance | Pilot indicators | Sign-ups, live, trial-to-paid | Needs Stripe + confirmation | Stripe | Low
AT-143 | Legal | Retention panel | Configured retention periods | Needs database | Database | Medium
AT-147 | Operations | Owner summary email | Periodic email from support@ | Needs email service | Email | Medium
AT-148 | Operations | How you compare | Anonymous median comparison | Needs approval + DB | David + DB | Low
AT-149 | Operations | Impersonation | View as this user | Needs David approval | David | Low
AT-150 | Product | Owner CSV export | Daily rows matching screen | Needs event store | AT-097 | Medium
AT-151 | Product | Weekly moderation report | Items received, closed, age | Needs audit tables | Database | Medium
UI-001 | Operations | /desk | KPI strip Open · Overdue · Due today · Unassigned | Needs WorkQueue | Database | Critical
UI-002 | Operations | /desk | Do next list sorted by SLA | Needs WorkQueue | Database | Critical
UI-003 | Operations | /desk/queues | Queue template with columns and drawer | Needs WorkQueue | Database | Critical
UI-004 | Operations | /desk/queues | Drawer with checks and decision | Needs WorkQueue | Database | Critical
UI-005 | Operations | /desk/people | Find a person with role filter | Needs server role check | Database | High
UI-006 | Operations | /desk/people | Staff roles tab | Needs permissions matrix | Database | High
UI-007 | Operations | /desk | Super user tiles and pilot glance | Needs WorkQueue + analytics | Database | High
UI-008 | Finance | /desk | Finance role tiles (trials, failed cards) | Needs Stripe + flag.money | Stripe | High
UI-009 | Operations | /desk/queues/verification | D15 evidence inline in drawer | Needs WorkQueue | Database | High
UI-010 | Operations | /desk/queues | Events <48h pinned as Urgent | Needs WorkQueue | Database | High
UI-011 | Operations | /desk/queues | Reports/Messages drawer actions | Needs WorkQueue + chat log | Database | Critical
UI-012 | Operations | /desk/queues | Promotions drawer with phone preview | Needs WorkQueue + push | Push service | High
UI-013 | Operations | /desk/safety | Frozen threads tab | Needs WorkQueue | Database | High
UI-014 | Operations | /desk/safety | Case drawer with Reveal identity | Needs WorkQueue + audit | Database | Critical
UI-015 | Operations | /desk/people | Roles matrix (read-only) | Needs permissions matrix | Database | High
UI-016 | Operations | /desk | Role-based tile visibility | Needs permissions matrix | Database | Critical
UI-017 | Operations | /desk | Moderator sees Queues and People only | Needs permissions matrix | Database | High
UI-018 | Operations | /desk | Safeguarding lead tiles | Needs WorkQueue | Database | Critical
UI-019 | Operations | /desk | Finance tiles hidden until Money on | Needs flag.money | Feature flags | High
UI-020 | Operations | /desk/safety | High-severity rows can't dismiss until claimed | Needs WorkQueue | Database | Critical
UI-021 | Operations | /desk | Moderator landing with verification tiles | Needs WorkQueue | Database | High
UI-022 | Operations | /desk | Pilot at a glance funnel + 16-area grid | Needs analytics | Database | High
UI-023 | Finance | /desk | Trials ending in 7 days / Ending today | Needs Stripe | Stripe | High
UI-024 | Operations | /desk/queues | Live counts and Claim / Escalate | Needs WorkQueue | Database | Critical
UI-025 | Operations | /desk/queues/verification | Approve auto-opens next item | Needs WorkQueue | Database | High
UI-026 | Operations | /desk/queues | History records reviewer role and time | Needs WorkQueue | Database | High
UI-027 | Operations | /desk/queues | Chat access log when opening thread | Needs WorkQueue + C6 | Database | Critical
UI-028 | Operations | /desk/queues | 1-per-7-days promo rule | Needs WorkQueue + push | Push service | High
UI-029 | Operations | /desk/safety | Role gating (Safeguarding lead only) | Needs permissions matrix | Database | High
UI-030 | Operations | /desk/safety | CSAM cases no preview or download | Needs WorkQueue | Database | Critical
UI-036 | Operations | /desk | UI-036 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-037 | Operations | /desk | UI-037 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-038 | Operations | /desk | UI-038 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-039 | Operations | /desk | UI-039 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-040 | Operations | /desk | UI-040 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-041 | Operations | /desk | UI-041 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-042 | Operations | /desk | UI-042 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-043 | Operations | /desk | UI-043 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-044 | Operations | /desk | UI-044 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-045 | Operations | /desk | UI-045 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-046 | Operations | /desk | UI-046 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-047 | Operations | /desk | UI-047 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-048 | Operations | /desk | UI-048 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-049 | Operations | /desk | UI-049 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-050 | Operations | /desk | UI-050 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-051 | Operations | /desk | UI-051 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-052 | Operations | /desk | UI-052 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-053 | Operations | /desk | UI-053 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-054 | Operations | /desk | UI-054 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-055 | Operations | /desk | UI-055 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-056 | Operations | /desk | UI-056 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-057 | Operations | /desk | UI-057 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-058 | Operations | /desk | UI-058 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-059 | Operations | /desk | UI-059 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-060 | Operations | /desk | UI-060 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-061 | Operations | /desk | UI-061 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-062 | Operations | /desk | UI-062 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-063 | Operations | /desk | UI-063 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-064 | Operations | /desk | UI-064 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-065 | Operations | /desk | UI-065 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-066 | Operations | /desk | UI-066 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-067 | Operations | /desk | UI-067 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-068 | Operations | /desk | UI-068 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-069 | Operations | /desk | UI-069 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-070 | Operations | /desk | UI-070 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-071 | Operations | /desk | UI-071 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-072 | Operations | /desk | UI-072 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-073 | Operations | /desk | UI-073 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-074 | Operations | /desk | UI-074 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-075 | Operations | /desk | UI-075 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-076 | Operations | /desk | UI-076 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-077 | Operations | /desk | UI-077 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-078 | Operations | /desk | UI-078 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-079 | Operations | /desk | UI-079 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-080 | Operations | /desk | UI-080 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-081 | Operations | /desk | UI-081 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-082 | Operations | /desk | UI-082 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-083 | Operations | /desk | UI-083 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-084 | Operations | /desk | UI-084 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-085 | Operations | /desk | UI-085 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-086 | Operations | /desk | UI-086 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-087 | Operations | /desk | UI-087 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-088 | Operations | /desk | UI-088 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-089 | Operations | /desk | UI-089 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-090 | Operations | /desk | UI-090 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-091 | Operations | /desk | UI-091 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-092 | Operations | /desk | UI-092 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-093 | Operations | /desk | UI-093 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-094 | Operations | /desk | UI-094 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-095 | Operations | /desk | UI-095 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-096 | Operations | /desk | UI-096 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-097 | Operations | /desk | UI-097 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-098 | Operations | /desk | UI-098 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-099 | Operations | /desk | UI-099 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-100 | Operations | /desk | UI-100 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-101 | Operations | /desk | UI-101 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-102 | Operations | /desk | UI-102 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-103 | Operations | /desk | UI-103 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-104 | Operations | /desk | UI-104 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-105 | Operations | /desk | UI-105 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-106 | Operations | /desk | UI-106 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-107 | Operations | /desk | UI-107 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-108 | Operations | /desk | UI-108 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-109 | Operations | /desk | UI-109 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-110 | Operations | /desk | UI-110 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-111 | Operations | /desk | UI-111 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-112 | Operations | /desk | UI-112 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-113 | Operations | /desk | UI-113 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-114 | Operations | /desk | UI-114 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-115 | Operations | /desk | UI-115 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-116 | Operations | /desk | UI-116 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-117 | Operations | /desk | UI-117 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-118 | Operations | /desk | UI-118 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-119 | Operations | /desk | UI-119 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-120 | Operations | /desk | UI-120 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-121 | Operations | /desk | UI-121 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-122 | Operations | /desk | UI-122 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-123 | Operations | /desk | UI-123 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-124 | Operations | /desk | UI-124 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-125 | Operations | /desk | UI-125 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-126 | Operations | /desk | UI-126 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-127 | Operations | /desk | UI-127 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-128 | Operations | /desk | UI-128 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-129 | Operations | /desk | UI-129 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-130 | Operations | /desk | UI-130 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-131 | Operations | /desk | UI-131 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-132 | Operations | /desk | UI-132 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-133 | Operations | /desk | UI-133 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-134 | Operations | /desk | UI-134 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-135 | Operations | /desk | UI-135 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-136 | Operations | /desk | UI-136 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-137 | Operations | /desk | UI-137 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-138 | Operations | /desk | UI-138 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-139 | Operations | /desk | UI-139 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-140 | Operations | /desk | UI-140 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-141 | Operations | /desk | UI-141 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-142 | Operations | /desk | UI-142 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-143 | Operations | /desk | UI-143 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-144 | Operations | /desk | UI-144 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-145 | Operations | /desk | UI-145 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-146 | Operations | /desk | UI-146 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-147 | Operations | /desk | UI-147 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-148 | Operations | /desk | UI-148 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-149 | Operations | /desk | UI-149 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-150 | Operations | /desk | UI-150 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-151 | Operations | /desk | UI-151 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-152 | Operations | /desk | UI-152 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-153 | Operations | /desk | UI-153 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-154 | Operations | /desk | UI-154 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-155 | Operations | /desk | UI-155 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-156 | Operations | /desk | UI-156 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-157 | Operations | /desk | UI-157 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-158 | Operations | /desk | UI-158 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-159 | Operations | /desk | UI-159 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-160 | Operations | /desk | UI-160 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-161 | Operations | /desk | UI-161 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-162 | Operations | /desk | UI-162 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-163 | Operations | /desk | UI-163 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-164 | Operations | /desk | UI-164 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-165 | Operations | /desk | UI-165 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-166 | Operations | /desk | UI-166 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-167 | Operations | /desk | UI-167 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-168 | Operations | /desk | UI-168 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-169 | Operations | /desk | UI-169 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-170 | Operations | /desk | UI-170 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-171 | Operations | /desk | UI-171 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-172 | Operations | /desk | UI-172 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-173 | Operations | /desk | UI-173 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-174 | Operations | /desk | UI-174 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-175 | Operations | /desk | UI-175 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-176 | Operations | /desk | UI-176 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-177 | Operations | /desk | UI-177 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-178 | Operations | /desk | UI-178 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-179 | Operations | /desk | UI-179 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-180 | Operations | /desk | UI-180 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-181 | Operations | /desk | UI-181 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-182 | Operations | /desk | UI-182 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-183 | Operations | /desk | UI-183 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-184 | Operations | /desk | UI-184 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-185 | Operations | /desk | UI-185 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-186 | Operations | /desk | UI-186 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-187 | Operations | /desk | UI-187 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-188 | Operations | /desk | UI-188 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-189 | Operations | /desk | UI-189 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-190 | Operations | /desk | UI-190 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-191 | Operations | /desk | UI-191 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-192 | Operations | /desk | UI-192 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-193 | Operations | /desk | UI-193 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-194 | Operations | /desk | UI-194 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-195 | Operations | /desk | UI-195 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-196 | Operations | /desk | UI-196 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-197 | Operations | /desk | UI-197 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-198 | Operations | /desk | UI-198 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-199 | Operations | /desk | UI-199 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-200 | Operations | /desk | UI-200 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-201 | Operations | /desk | UI-201 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-202 | Operations | /desk | UI-202 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-203 | Operations | /desk | UI-203 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-204 | Operations | /desk | UI-204 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-205 | Operations | /desk | UI-205 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-206 | Operations | /desk | UI-206 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-207 | Operations | /desk | UI-207 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-208 | Operations | /desk | UI-208 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-209 | Operations | /desk | UI-209 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-210 | Operations | /desk | UI-210 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-211 | Operations | /desk | UI-211 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-212 | Operations | /desk | UI-212 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-213 | Operations | /desk | UI-213 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-214 | Operations | /desk | UI-214 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-215 | Operations | /desk | UI-215 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-216 | Operations | /desk | UI-216 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-217 | Operations | /desk | UI-217 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-218 | Operations | /desk | UI-218 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-219 | Operations | /desk | UI-219 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-220 | Operations | /desk | UI-220 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-221 | Operations | /desk | UI-221 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-222 | Operations | /desk | UI-222 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-223 | Operations | /desk | UI-223 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-224 | Operations | /desk | UI-224 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium
UI-225 | Operations | /desk | UI-225 deferred – needs WorkQueue or permissions matrix | Needs WorkQueue / permissions matrix / database | Database | Medium

## Notes
Deferred items – The Common Community Ltd
These items were deferred during the AT-001 to AT-153 review because they need a live database, Stripe, an API key, or another external service.
Return to this list once the database is connected (see Database_Connection_Guide.docx).
Hosting: FastHosts (fasthosts.co.uk)
Prepared: 15 October 2026